Autism All Grown Up

The Autism Nexus of Oregon

Ariel Balter

6/3/24

Contents

# 1.



# 2. Mission

The mission of Autism All Grown Up (AAGU) is to empower autistic adults in Oregon by serving as a nexus that provides accessible information, resources, and services tailored to their unique needs. By bridging gaps in the existing infrastructure, we connect and interconnect the adult autistic community and their supporters, facilitate information exchange, and promote collaboration. This ensures that autistic individuals can access the support and opportunities they need to thrive, enhancing their well-being and independence throughout the state.

# 3. Executive Summary

## Background

Dr. Ariel Balter, an experienced scientist and data analyst, was diagnosed with ADHD and ASD later in life and is raising a teenager with both diagnoses. His desire to understand these challenges led him to study the scientific and social aspects of neurodiversity. Recent changes driven by autistic self-advocates and researchers have reshaped our understanding of autism, revealing significant gaps in support for autistic adults. These changes have led to controversies and arguments that are still unfolding, emphasizing the evolving nature of the understanding of autism.

Through his personal journey and interactions with the local autistic community, Dr. Balter identified significant gaps in services, support, and understanding for autistic adults without intellectual disabilities. He was struck by the level of unmet need he heard from his peers—people with skills, education, and abilities but struggling for reasons related to autism. These personal experiences led Dr. Balter to found Autism All Grown Up (AAGU) to address these gaps.

## Goals

The organization has four key objectives:

1. Facilitate connections and collaboration within the adult autistic community
2. Identify the unmet needs of autistic adults and report on the causes
3. Provide accurate, accessible, and up-to-date information and resources *for* autistic adults
4. Provide accurate, accessible, and up-to-date information and resources *about* autism and *about* the autistic community

## Autism All Grown Up

Autism is all grown up, and it isn’t pretty. The phrase “All Grown Up” captures the bittersweet realization that often occurs when one encounters an individual they knew as a child, only to find that their preconceived notions no longer fit the adult standing before them.

For decades, autism was seen as a developmental challenge that primarily affected children. Outdated notions of what constitutes genuine autism have cause adults to be overlooked by many people. Because so little research has acknowledged the lives of adults with autism, we know close to nothing about what successful adult development looks like. Some existing research suggests that autistic adults face reduced life expectancy, increased risk for physical disability, and an earlier onset of age-related cognitive concerns. Late-identified and never-identified autistic adults face unique challenges with respect to aging, and most of these “lost generations” (Wright 2015) have not yet even been counted.

## The Nexus Approach

Rather than working on advocacy, Dr. Balter feels he can more directly serve the autistic community in Oregon by solving problems on the ground. Systemic and societal problems can only be addressed through advocacy. But many of the real-world problems faced by supporting existing infrastructure by increasing the connectivity and information flow. Rather than being a hub that consumes resources and provides services, AAGU will catalyze and strengthen relationships around it to form a *nexus*.

# 4. Autism in 2024

## The New World of Autism

Recent advancements in autism research, largely driven by autistic self-advocates and researchers, have highlighted the need for a paradigm shift in understanding and supporting autistic individuals. Key findings include:

* **Navigational Challenges:** Most autistic individuals are not intellectually disabled but face substantial challenges navigating society. Navigating society feels like being a left-handed person using right-handed scissors: difficult and unwieldy at best.
* **Lifelong Condition:** Autism is a lifelong neurological difference, not a disorder to be cured. There are roughly the same percentage of autistic adults as children, but there are four times as many adults as children.
* **Neurodiversity:** The neurodiversity paradigm recognizes autism as a natural variation in human neurology. Statistically, fewer than half of autistic people are intellectually disabled but may face challenges navigating a neurotypical world. A significant population of autistic adults has needs that are often unmet.
* **Focus Gaps:** Research and services have predominantly focused on children and intellectually disabled adults, leaving a gap for others. We have failed, and continue to fail, to study autistic life after high school.
* Autism is a lifelong neurological difference, not a disorder to be cured.
* Most autistic people are not intellectually or physically disabled but may face substantial challenges.
* The neurodiversity paradigm recognizes autism as a natural variation in human neurology. For many autistic people, the hardest part about being autistic is navigating a neurotypical world.
* Research and services have predominantly focused on children leaving out adults, especially those without profound disabilities.

## Lost Generations of Autistic Adults

Autistic adults face unique challenges that are often overlooked, such as navigating social and employment environments not designed for neurodivergent individuals. Autistic adults without intellectual disabilities often face a lack of access to appropriate healthcare and support services.

Autistic adults perceived as having lower support needs face a conundrum. While they rarely qualify for existing systems of support, most face significant challenges that are often overlooked, dismissed, or disbelieved. Most autistic people will tell you that the hardest part about being autistic isn’t being autistic but navigating a neurotypical world that includes unconscious bias and ableism. Research backs this up, indicating that discrimination, not autism, is a significant barrier in the workplace.

Autistic adults face unique challenges that are often overlooked, such as navigating social and employment environments not designed for neurodivergent individuals. Key issues include:

Despite these challenges, many autistic adults possess valuable skills, talents, and perspectives that society misses out on by not acknowledging their needs, hearing their voices, and making room for them at the table.

# 5. Autism All Grown Up (AAGU): A Nexus for Change

## Origin

AAGU was born out of Dr. Balter’s desire to use his personal experiences and analytical skills to help his newfound community. By conducting root cause analyses and working with local organizations, he identified key areas where AAGU could make an immediate impact, such as:

* Creating accessible guides for obtaining adult autism diagnoses through Oregon’s Medicaid and Vocational Rehabilitation systems
* Establishing The Uncommons, autism-friendly co-working and community spaces
* Improving online resources for autistic adults and providing consulting services to others to do the same
* Participating in data analysis and research efforts to better understand the needs of autistic adults in Oregon

## What We Have Started

AAGU has already made strides in achieving its objectives through initiatives such as:

* Partnering with Health Share Oregon to create guides for accessing autism assessments through Medicaid and developing a template Letter of Medical Necessity to facilitate evaluations through I/DD and Vocational Rehab programs
* Securing temporary spaces for The Uncommons, autism-friendly co-working and community spaces
* Consulting with the Autism Society of Oregon to improve their online resources
* Participating in the Oregon Commission on Autism Spectrum Disorder’s data working group

## Goals

Autism All Grown Up (AAGU) seeks to activate and empower the autistic community in Oregon by improving communication channels and information resources. Our immediate actions include:

* Establishing The Uncommons, a meeting and coworking space for autistic adults
* Creating comprehensive guides on navigating healthcare, employment, and social services
* Building partnerships with local organizations to enhance service delivery
* Participating in data analysis and research to inform policy and advocacy efforts

Our growth plan consists of three phases:

1. Seed (Weeks 1-8): Set up organizational structure, solicit initial funds, establish community presence, and build initial partnerships
2. Sprout (Weeks 9-26): Continue building community connections, develop The Uncommons, create informational materials, and identify large funding opportunities
3. Grow (Beyond Week 26): Expand The Uncommons, apply for large grants, build information and communication infrastructure, and establish a sustainable model for ongoing operations

## Growth Plan

Our growth plan consists of three phases:

**1. Seed (Weeks 1-8)**

* **Budget:** $2,310/week
* **Effort:** 1.5 FTE
* **Actions:**
  + Set up organizational structure
  + Solicit initial funds
  + Establish community presence
  + Build initial partnerships

**2. Sprout (Weeks 9-26)**

* **Budget:** $4,620/week
* **Effort:** 2.75 FTE
* **Actions:**
  + Continue building community connections
  + Develop The Uncommons
  + Create informational materials
  + Identify large funding opportunities

**3. Grow (Beyond Week 26)**

* **Budget:** $6,468/week
* **Effort:** 4.25 FTE
* **Actions:**
  + Expand The Uncommons
  + Apply for large grants
  + Build information and communication infrastructure
  + Establish a sustainable model for ongoing operations

By establishing a comprehensive support system for autistic adults, AAGU aims to improve their quality of life, promote independence, and foster a sense of community and belonging. Through a phased growth plan, AAGU will continue to expand its reach and impact, with a strong emphasis on hiring autistic individuals and providing them with meaningful employment opportunities. By leveraging the strengths and talents of the autistic community, AAGU is uniquely positioned to create lasting, positive change for autistic adults in Oregon.

# 6. Funding

We are poised to launch a GoFundMe crowdsource campaign as soon as we have our nonprofit status confirmed by ARRO. We hope to raise seed money of $2k-$3k per week to jump start formal operations \*\*\*\*\*\*\*\*\*\*\*\*\* next $34k for our 8-week Sprout phase. We hope to launch the Sprout phase within our first month.

A key element of our first 8 weeks of formal operation (Sprout) will be to create a calendar of funding deadlines and communicate with funders to prioritize our initial grant-writing efforts. It will also be crucial that we complete the initial projects we have started during the Sprout phase to demonstrate our effectiveness to potential supporters. At the end of the Sprout phase, we will report to our umbrella organizations and all funders/sponsors.

We are on the verge of launching a GoFundMe crowdsource campaign, a crucial step that hinges on our nonprofit status being confirmed by ARRO. The urgency is palpable as we aim to raise a substantial seed fund of $2k-$3k per week, a total of $ 34k, to kickstart our formal operations. This will pave the way for our 8-week Sprout phase, which we plan to initiate within our first month.

Our initial 8 weeks of formal operation, known as the Sprout phase, are meticulously planned. We will create a comprehensive calendar of funding deadlines and engage in proactive communication with funders to prioritize our grant-writing efforts. Equally important is the completion of our initial projects during this phase, which will serve as tangible proof of our effectiveness to potential supporters. At the end of the Sprout phase, we will provide a detailed report to our umbrella organizations and all funders/sponsors.

We have already identified almost 100 grants and sponsorships for which we meet the basic requirements. These include grants from the State of Oregon (e.g. Oregon Health Authority), Oregon healthcare companies (Legacy, Pacific Source, Cambia, etc.), and a mixture of private and public foundations and trusts. We have missed the 2024 funding cycle for some of these, but many have multiple cycles per year or do not run in cycles. Some of these are small pots of money, and others regularly award hundreds of thousands of dollars. We will also collect sliding-scale fees for using *The Uncommons* co-working spaces.

During our Grow phase, we hope to show that we can collect, analyze, and disseminate information for and about the adult autistic community with a very high level of capacity and efficiency. We hope this expertise will enable us to secure outside contracts as subject matter experts, analysts, and report writers, providing another avenue for revenue. We will complete the Grow phase with a report to our umbrella organization and our financial supporters.

# 7. Budget

Autism All Grown Up will place a strong emphasis on hiring autistic and neurodiverse Oregon adults and paying them a market wage. The wages will be at the low end during the initial Seed and Sprout phases and increase during the later phases. The hourly rates shown represent full compensation on a 1099 and do not include benefits. We will make necessary adjustments when we are able to provide benefits as well.

We have created our budget estimate based on the minimum staffing we believe can meet our performance goals combined with market-rate salary estimates from ZipRecruiter (<https://www.ziprecruiter.com/Salaries>) for approximate job titles in the Portland, OR area (see [Appendix 2: Representative Salaries](#appendix-2-representative-salaries)). We project a budget of approximately $150,000 for the first six months (26 weeks) of operation.

## **Seed**

### Staffing

| **Res ponsibility** | **FTE** | **Description** |
| --- | --- | --- |
| Organizing and Directing | 0.75 | Implement business systems–payrol, formal job descriptions, insurance, etc. Hold regular meetings with select partner organizations and individuals. Solicit and apply for funding for Sprout phase. |
| Coworking space manager | 0.25 | Research how coworking spaces run. Create a budget and game plan for initial set-up. Begin planning marketing and promotion. |
| Research support | 0.25 | Collect and organize information. Writing. |
| Web Development | 0.25 | Design and build website. |
| **Total** | **1.50** |  |

### Budget

| **Respo nsibility** | **FTE** | **Rate** | **Weekly Total** | **Overhead (10%)** |
| --- | --- | --- | --- | --- |
| Organizing and Directing | 0.75 | $40.00 | $1,200.00 | $120.00 |
| Coworking space manager | 0.25 | $30.00 | $300.00 | $30.00 |
| Research support | 0.25 | $30.00 | $300.00 | $30.00 |
| Web Development | 0.25 | $30.00 | $300.00 | $30.00 |
| Subtotal per week |  |  | $2,100.00 | $210.00 |
| **Total per week** |  |  | **$ 2,310.00** |  |

## **Sprout**

### **Staffing**

| **R esponsibility** | **FTE** | **Description** |
| --- | --- | --- |
| Organizing and Directing | 0.75 | Complete current information product projects. Investigate access gaps. Locate resources. Continue building relationships. Oversee and participate in research on community resources and funding opportunities. |
| Data engineering | 0.50 | Create databases. Research portal design. |
| Coworking space manager | 0.50 | Research how coworking spaces run. Solicit community feedback. Run trails. |
| Research support | 0.50 | Collect and organize information. Writing. |
| Web Development | 0.50 | Design and build website. |
| **Total** | **2.75** |  |

### **Budget**

| **Respo nsibility** | **FTE** | **Rate** | **Weekly Total** | **Overhead (10%)** |
| --- | --- | --- | --- | --- |
| Organizing and Directing | 0.75 | $50.00 | $1,500.00 | $150.00 |
| Data engineering | 0.50 | $45.00 | $900.00 | $90.00 |
| Coworking space manager | 0.50 | $30.00 | $600.00 | $60.00 |
| Research support | 0.50 | $30.00 | $600.00 | $60.00 |
| Web Development | 0.50 | $30.00 | $600.00 | $60.00 |
| Subtotal per week |  |  | $4,200.00 | $420.00 |
| Total per week |  |  | $4,620.00 |  |
| **Total for 8 weeks** |  |  | **$3 3,600.00** |  |

## Grow

### **Staffing**

| **Res ponsibility** | **FTE** | **Description** |
| --- | --- | --- |
| Organizing and Directing | 1.00 | Seek out partners and funding opportunities. Work with stakeholders to define contract requirements. Direct grant writing. Meet regularly with partner organizations and individuals. |
| Data engineering | 0.30 | Maintain databases and portal. Assist with analysis and reporting. |
| Jr. Data management | 0.20 | Collect data. Enter data. Basic reporting. |
| Research and analysis | 0.50 | Perform analysis and generate reports. Lead grant-writing efforts. Be responsible for obtaining necessary approvals, meeting all grant requirements, and submitting on time. |
| Research support (Jr.) | 0.50 | Locate resources. Collect and organize information. Conduct surveys. |
| Web Development | 0.25 | Maintain website. |
| Coworking space manager | 1.00 | Determine best practices. Maintain the physical space. Set and enforce policies. |
| Coworking space attendant | 0.50 | Oversee operation. |
| **Total** | **4.25** |  |

### **Budget**

| **Respo nsibility** | **FTE** | **Rate** | **Weekly Total** | **Overhead (10%)** |
| --- | --- | --- | --- | --- |
| Organizing and Directing | 0.75 | $65.00 | $1,950.00 | $195.00 |
| Data engineering | 0.30 | $45.00 | $540.00 | $54.00 |
| Jr. Data management | 0.20 | $30.00 | $240.00 | $24.00 |
| Research and analysis | 0.50 | $45.00 | $900.00 | $90.00 |
| Research support (Jr.) | 0.50 | $30.00 | $600.00 | $60.00 |
| Web Development | 0.25 | $45.00 | $450.00 | $45.00 |
| Coworking space manager | 0.75 | $40.00 | $1,200.00 | $120.00 |
| Coworking space attendant | 0.50 | $25.00 | $500.00 | $50.00 |
| Subtotal per week |  |  | $5,880.00 | $588.00 |
| Total per week |  |  | $6,468.00 |  |
| **Total for 18 weeks** |  |  | **$11 6,424.00** |  |

# 8.

# 9. References

Angell, Amber M., Allison Empey, and Katharine E. Zuckerman. 2018. “Chapter Four - A Review of Diagnosis and Service Disparities Among Children With Autism From Racial and Ethnic Minority Groups in the United States.” In *International Review of Research in Developmental Disabilities*, edited by Robert M. Hodapp and Deborah J. Fidler, 55:145–80. International Review of Research in Developmental Disabilities. Academic Press. <https://doi.org/10.1016/bs.irrdd.2018.08.003>.

Cassidy, Sarah, Jane Goodwin, Ashley Robertson, Heather Cogger-Ward, and Jacqui Rodgers. 2021. *Autism Community Priorities for Suicide Prevention*. <https://doi.org/10.13140/RG.2.2.16668.82568>.

Churchard, Alasdair, Morag Ryder, Andrew Greenhill, and William Mandy. 2019. “The Prevalence of Autistic Traits in a Homeless Population.” *Autism: The International Journal of Research and Practice* 23 (3): 665–76. <https://doi.org/10.1177/1362361318768484>.

D’Mello, Anila M., Isabelle R. Frosch, Cindy E. Li, Annie L. Cardinaux, and John D. E. Gabrieli. 2022. “Exclusion of Females in Autism Research: Empirical Evidence for a ‘Leaky’ Recruitment-to-Research Pipeline.” *Autism Research* 15 (10): 1929–40. <https://doi.org/10.1002/aur.2795>.

Fombonne, Eric, and Katharine E. Zuckerman. 2022. “Clinical Profiles of Black and White Children Referred for Autism Diagnosis.” *Journal of Autism and Developmental Disorders* 52 (3): 1120–30. <https://doi.org/10.1007/s10803-021-05019-3>.

George, Rita, and Mark A Stokes. 2018. “Gender Identity and Sexual Orientation in Autism Spectrum Disorder.” *Autism* 22 (8): 970–82. <https://doi.org/10.1177/1362361317714587>.

George, R., and M.a. Stokes. 2018. “Sexual Orientation in Autism Spectrum Disorder.” *Autism Research* 11 (1): 133–41. <https://doi.org/10.1002/aur.1892>.

Kargas, N., K. M. Harley, A. Roberts, and S. Sharman. 2019. “Prevalence of Clinical Autistic Traits Within a Homeless Population: Barriers to Accessing Homeless Services.” *Journal of Social Distress and the Homeless* 28 (2): 90–95.

Lodi-Smith, Jennifer, Elyse J. Ponterio, Nicky J. Newton, Michael J. Poulin, Erica Baranski, and Susan Krauss Whitbourne. 2021. “The Codevelopment of Generativity and Well-Being into Early Late Life.” *Psychology and Aging* 36 (3): 299–308. <https://doi.org/10.1037/pag0000446>.

Lodi-Smith, Jennifer, Jonathan D. Rodgers, Valeria Marquez Luna, Sarah Khan, Caleb J. Long, Karl F. Kozlowski, James P. Donnelly, Christopher Lopata, and Marcus L. Thomeer. 2021. “The Relationship of Age with the Autism-Spectrum Quotient Scale in a Large Sample of Adults.” *Autism in Adulthood* 3 (2): 147–56. <https://doi.org/10.1089/aut.2020.0010>.

Loomes, Rachel, Laura Hull, and William Polmear Locke Mandy. 2017. “What Is the Male-to-Female Ratio in Autism Spectrum Disorder? A Systematic Review and Meta-Analysis.” *Journal of the American Academy of Child and Adolescent Psychiatry* 56 (6): 466–74. <https://doi.org/10.1016/j.jaac.2017.03.013>.

Muskens, Jet B., Fleur P. Velders, and Wouter G. Staal. 2017. “Medical Comorbidities in Children and Adolescents with Autism Spectrum Disorders and Attention Deficit Hyperactivity Disorders: A Systematic Review.” *European Child & Adolescent Psychiatry* 26 (9): 1093–103. <https://doi.org/10.1007/s00787-017-1020-0>.

Ohl, Alisha, Mira Grice Sheff, Sarah Small, Jamie Nguyen, Kelly Paskor, and Aliza Zanjirian. 2017. “Predictors of Employment Status Among Adults with Autism Spectrum Disorder.” *Work (Reading, Mass.)* 56 (2): 345–55. <https://doi.org/10.3233/WOR-172492>.

Wright, Jessica. 2015. “Autism’s Lost Generation.”

# Appendix A — What is the Autism Spectrum?

|  |
| --- |
| What the autism spectrum means. |

# Appendix A — The Services Cliff

* Services Cliff: Young autistic adults also face significant challenges transitioning out of high school, often referred to as the “services cliff.” This sudden drop-off in support can lead to difficulties in finding meaningful work, pursuing higher education, and living independently. [<https://drexel.edu/autismoutcomes/blog/overview/2015/August/falling-off-the-services-cliff/>].

Transition to Adulthood This problem does not just affect existing adults. The sudden drop-off of support upon graduating high school has become known as the services cliff. One of the biggest worries faced by both parents of autistic people and young autistic people themselves is what will happen after they graduate from high school. Will they be offered meaningful work in tolerant and respectful environments? Will they be able to earn enough to live independently? Will they find open doors in trade schools or collegFes and be offered the support they might need?

# Appendix A — Access to Medical Care

There is an immense amount of work to do to help prepare the aging autistic adult community and a poorly informed medical system to successfully face these challenges right now and in the coming decades. Fortunately, there are also many skilled, intelligent, creative, compassionate, and hard-working people in the autistic community who are ready and capable of doing this work. And they are the right people to do it.

# Appendix A — Medical Training

Lack of training for healthcare providers

# Appendix A — Autism Research Funding Priorities

Despite the fact that advocates and researchers have been pushing for decades to have autism research funding focus more on quality of life and less on “prevention and cure”, the trend has only gotten worse.




Figure 2. Data from [Interagency Autism Coordination Committee](https://iacc.hhs.gov/funding/data/)

# Appendix A — Intersectionally marginalized Groups

All of these problems compound for members of intersectional populations who may already be marginalized along other dimensions. Many researchers believe that autism is (Fombonne and Zuckerman 2022), particularly in Black communities (Angell, Empey, and Zuckerman 2018), as well as for (D’Mello et al. 2022). Meanwhile, fluidity in gender and sexual orientation Rita George and Stokes (2018) is more highly represented among autistic people. Little research has been done to assess how autism uniquely affects people in these different subgroups.

# Appendix A — Physical and Mental Health

* Health and Well-being: Autistic adults experience higher rates of mental health issues, physical health disparities, and substantially elevated suicide risk [<https://www.nature.com/articles/s41583-021-00463-7>, <https://pubmed.ncbi.nlm.nih.gov/33407027/>].
* Social Isolation: Negative social experiences can lead to self-isolation, exacerbating feelings of loneliness and exclusion (Loomes, Hull, and Mandy 2017)

Across a variety of health domains, autistic people fare worse Lodi-Smith, Rodgers, et al. (2021). Additionally, we are exposed to risks that are not of primary concern for most people (Muskens, Velders, and Staal 2017). These include autoimmune dysregulation of many kinds, autonomic dysregulation, connective tissue disorders, gastrointestinal disorders, and many other areas of health concerns. A lack of understanding regarding these differences, coupled with communication barriers and false notions about autism all collude to create barriers to accessing health services and care.

# Appendix A — Unemployment

* Employment: Many autistic adults face difficulties finding and maintaining employment due to biases and lack of accommodations. In a study of 254 autistic adults, 77% reported difficulties applying for jobs, and only 16% are in full-time paid work [<https://www.ncbi.nlm.nih.gov/pmc/articles/PMC5215190/>, <https://www.frontiersin.org/articles/10.3389/fpsyg.2021.719827/full>].

# Appendix A — Homelessness

Barriers to entry to the workplace as well as challenges and holding jobs due to ablest attitudes or inflexible policies put us at risk of severe financial strain (Ohl et al. 2017). This coupled with the possibility of reduced social support all increase our risk of exposure to homelessness. The few studies that attempted to investigate autism in homeless populations suggest that rates of autism in homeless populations is much higher than that observed in the general public, and may be ten times higher (Churchard et al. 2019). Autistic people additionally face extra barriers in accessing the few services for unhoused people. Environments created with the intention of providing support may be aversive or even harmful for autistic people (Kargas et al. 2019).

# Appendix A — Suicide

As a group, their suicide risk may be two to seven times higher than the risk for youth and adults who do not have autism. When researchers took into account psychiatric conditions that increase suicide risk, such as depression, anxiety, and substance abuse disorders, autistic people still had a higher risk than the comparison group [@|autism2022]. The International Society for Autism Research says “Suicide in autism is a hidden crisis, overlooked by policymakers, clinicians and researchers worldwide.” and highlights three barriers: a lack of evidence-based assessment tools and interventions to identify and treat suicidal thoughts and behaviors; a lack of access to mental health services10 and exclusion from conversations about policies and guidelines that affect autistic people.” (Cassidy et al. 2021)

# Appendix B — Funding

We are poised to launch a GoFundMe crowdsource campaign as soon as we have our nonprofit status confirmed by ARRO. We hope to raise seed money of $2k-$3k per week to jump start formal operations \*\*\*\*\*\*\*\*\*\*\*\*\* next $34k for our 8-week Sprout phase. We hope to launch the Sprout phase within our first month.

A key element of our first 8 weeks of formal operation (Sprout) will be to create a calendar of funding deadlines and communicate with funders to prioritize our initial grant-writing efforts. It will also be crucial that we complete the initial projects we have started during the Sprout phase to demonstrate our effectiveness to potential supporters. At the end of the Sprout phase, we will report to our umbrella organizations and all funders/sponsors.

We are on the verge of launching a GoFundMe crowdsource campaign, a crucial step that hinges on our nonprofit status being confirmed by ARRO. The urgency is palpable as we aim to raise a substantial seed fund of $2k-$3k per week, a total of $ 34k, to kickstart our formal operations. This will pave the way for our 8-week Sprout phase, which we plan to initiate within our first month.

Our initial 8 weeks of formal operation, known as the Sprout phase, are meticulously planned. We will create a comprehensive calendar of funding deadlines and engage in proactive communication with funders to prioritize our grant-writing efforts. Equally important is the completion of our initial projects during this phase, which will serve as tangible proof of our effectiveness to potential supporters. At the end of the Sprout phase, we will provide a detailed report to our umbrella organizations and all funders/sponsors.

We have already identified almost 100 grants and sponsorships for which we meet the basic requirements. These include grants from the State of Oregon (e.g. Oregon Health Authority), Oregon healthcare companies (Legacy, Pacific Source, Cambia, etc.), and a mixture of private and public foundations and trusts. We have missed the 2024 funding cycle for some of these, but many have multiple cycles per year or do not run in cycles. Some of these are small pots of money, and others regularly award hundreds of thousands of dollars. We will also collect sliding-scale fees for using *The Uncommons* co-working spaces.

During our Grow phase, we hope to show that we can collect, analyze, and disseminate information for and about the adult autistic community with a very high level of capacity and efficiency. We hope this expertise will enable us to secure outside contracts as subject matter experts, analysts, and report writers, providing another avenue for revenue. We will complete the Grow phase with a report to our umbrella organization and our financial supporters.

# Appendix C — Appendix 1: Glossary

| **Term** | **Definition** |
| --- | --- |
| **ADLs** | When a person applies for Medicaid long-term care services in Oregon, we look at how much help they need to perform Activities of Daily Living. Because funding is limited, we use this information (called a service priority level) to decide who is eligible for services. Activities of Daily Living are the basic personal activities all of us need to do that are essential for health and safety. These activities are defined in OAR 411-015-0006 [https://www.oregon.gov/odhs/aging-disability-servi ces/p ages/adl.aspx](https://www.oregon%20.%20gov/odhs/aging-disability-services/pages/adl.aspx) |
| * \*A lexithymia\*\* | Alexithymia is the inability for someone to recognize, identify, and describe feelings or emotions. It is sometimes referred to as emotional blindness. [[https://www.health.com/alexithymia-8361963]{.unde r line}](https://www.health.com/alexithymia-8361963) |
| **Asperger’s Syndrome** | Asperger’s syndrome (sometimes called high-functioning autism) is part of a wide diagnosis called autism spectrum disorder (ASD). Since 2013, Asperger’s syndrome is replaced by the broader diagnosis of ASD within the Diagnostic and Statistical Manual of Mental Disorders (DSM-5) revised criteria. [h t tps://my.clevelandclinic.org/health/diseases/6436- asper ger-syndrome](https://my.clevelan%20d%20clinic.org/health/diseases/6436-asperger-syndrome) |
| **Co-Occurring Conditions** | The preferred term in the autistic community as a replacement for “comorbid” for conditions, traits, and behaviors that are commonly found along with autism. |
| **Double Empathy** | Double empathy refers to how:  1. It is easier to understand the mindset of people who are similar to you  2. It is more difficult to understand the mindset of those who are different from you  This concept was specifically developed by the autistic autism researcher Damian Milton to explain how autistics and neurotypicals empathize with each other. It explains how allistics (non-autistics) struggle to understand the lived experiences of autistics and autistics struggle to understand the lived experiences of allistics. Likewise, autistics are better at understanding other autistics and allistics are better at understanding other allistics. [https://embrace-autism.com/autism-and-the-do uble- empathy-problem/](https://embrace%20-%20autism.com/autism-and-the-double-empathy-problem/) |
| **Dyslexia** | Dyslexia is a specific learning difficulty which primarily affects reading and writing skills. However, it does not only affect these skills. Dyslexia is actually about information processing. Dyslexic people may have difficulty processing and remembering information they see and hear, which can affect learning and the acquisition of literacy skills. Dyslexia can also impact on other areas such as organisational skills. It is important to remember that there are positives to thinking differently. Many dyslexic people show strengths in areas such as reasoning and in visual and creative fields. [https : //www.bdadyslexia.org.uk/dyslexia/about-dyslexia/w hat-i s-dyslexia](https://www.bdadyslex%20i%20a.org.uk/dyslexia/about-dyslexia/what-is-dyslexia) |
| **Dyspraxia** | Dyspraxia is a term that refers to lifelong trouble with movement and coordination. It’s not a formal diagnosis. But you may still hear people use this term, especially in the U.K. The formal diagnosis is developmental coordination disorder (DCD). [https://www.understood.org/en/articles /unde rstanding-dyspraxia](https://www.%20u%20nderstood.org/en/articles/understanding-dyspraxia) |
| **fMRI** | Functional MRI is a type of MRI scan that can show which areas of your brain are most active. Tracking and comparing that activity to what you were doing at the time can help “map” your brain activity. It’s most often used for planning surgery or similar procedures in the brain. [https://my.cl e velandclinic.org/health/diagnostics/25034-function al-mr i-fmri](https://my.clevelandclini%20c%20.org/health/diagnostics/25034-functional-mri-fmri) |
| **Gender identity** | One’s innermost concept of self as male, female, a blend of both or neither – how individuals perceive themselves and what they call themselves. One’s gender identity can be the same or different from their sex assigned at birth. [[http s ://www.hrc.org/resources/sexual-orientation-and-ge n der-identity-terminology-and-definitions]{.underli ne}](https://www.hrc.org/resources/sexual-orientati%20o%20n-and-gender-identity-terminology-and-definitions) |
| **Genome** | The genome is the entire set of DNA instructions found in a cell. In humans, the genome consists of 23 pairs of chromosomes located in the cell’s nucleus, as well as a small chromosome in the cell’s mitochondria. A genome contains all the information needed for an individual to develop and function. [https:// ww w.genome.gov/genetics-glossary/Genome](https://www.genome.gov/genetics-glossary/Genome) |
| **Health Share Oregon** | One of Oregon’s Community Care Organizations (CCO) for OHP. [https://www.healthshareoregon.org /](https://www.healthshareoregon.org/) |
| **I/DD** | [Oregon Department of Human Services: Intellectual and Developmental Disabilities.](h%20ttps://www.oregon.gov/odhs/idd/pages/default.aspx) |
| **Letter of Medical Necessity** | A Letter of Medical Necessity (LMN) is the written explanation from the treating physician describing the medical need for services, equipment, or supplies to assist the claimant in the treatment, care, or relief of their accepted work-related illness(es). <https://www.dol> . gov/sites/dolgov/files/OWCP/energy/regs/compliance / Outreach/Outreach\_Presentation/lmn\_mba06222022.pdf |
| **Ne urodivergent** |  |
| **Ne urodiversity** |  |
| **Non-Speaking** | When an autistic person doesn’t speak, it’s known as nonspeaking autism. You may also see it described as nonverbal autism. However, the term nonverbal isn’t completely accurate, since it means “without words. Even if an autistic person is nonspeaking, they may still use words in other ways (such as in writing). They may also understand the words that are spoken to them or that they overhear. https: / /www.healthline.com/health/autism/nonverbal-autism |
| **OCD** | Obsessive-compulsive disorder (OCD) is a disorder in which people have recurring, unwanted thoughts, ideas or sensations (obsessions). To get rid of the thoughts, they feel driven to do something repetitively (compulsions). The repetitive behaviors, such as hand washing/cleaning, checking on things, and mental acts like (counting) or other activities, can significantly interfere with a person’s daily activities and social interactions. <https://ww> w .psychiatry.org/patients-families/obsessive-compul s ive-disorder/what-is-obsessive-compulsive-disorder |
| **ODDS** | Oregon [Office of Developmental Disabilities Services](https://ww%20w%20.oregon.gov/odhs/agency/pages/odds.aspx?jump=true) |
| **OHP** | [Oregon Health Plan: Oregon Medicaid](h%20t%20tps://www.oregon.gov/oha/hsd/ohp/pages/index.aspx) |
| **Services Cliff** | Many high school students on the autism spectrum get help through special education – most commonly including speech-language therapy, service coordination/case management, behavior management, and special transportation. Each student has a team that works with the student and family to decide which services are needed to prepare him or her for young adulthood, and federal law requires schools to offer the necessary services. Sounds like a good plan for how to help vulnerable youth through a challenging period of life. But then, following the last day of high school, the legal mandate for help suddenly ends. [[https://drexel.edu/autismoutcomes/blog/overvi e w/2015/August/falling-off-the-services-cliff/]{.un derli ne}](https://drexel.edu/autismoutcomes/blog/ov%20e%20rview/2015/August/falling-off-the-services-cliff/) |
| **Sexual orientation** | An inherent or immutable enduring emotional, romantic or sexual attraction to other people. Note: an individual’s sexual orientation is independent of their gender identity. [[http s ://www.hrc.org/resources/sexual-orientation-and-ge n der-identity-terminology-and-definitions]{.underli ne}](https://www.hrc.org/resources/sexual-orientati%20o%20n-and-gender-identity-terminology-and-definitions) |
| * \*S ynesthesia\*\* | Synesthesia is when your brain routes sensory information through multiple unrelated senses, causing you to experience more than one sense simultaneously. Some examples include tasting words or linking colors to numbers and letters. It’s not a medical condition, and many people find it useful to help them learn and remember information. <https://my.cl> e velandclinic.org/health/symptoms/24995-synesthesia |
| **Theory of Mind** | In psychology, theory of mind refers to the capacity to understand other people by ascribing mental states to them. A theory of mind includes the knowledge that others’ beliefs, desires, intentions, emotions, and thoughts may be different from one’s own. Possessing a functional theory of mind is crucial for success in everyday human social interactions. People utilize a theory of mind when analyzing, judging, and inferring others’ behaviors. The discovery and development of theory of mind primarily came from studies done with animals and infants. Factors including drug and alcohol consumption, language development, cognitive delays, age, and culture can affect a person’s capacity to display theory of mind. Having a theory of mind is similar to but not identical with having the capacity for empathy or sympathy. <https://en.wikipedia.org/wiki/Theory_of_mind> |

# Appendix C —

# Appendix D — Appendix 2: Representative Salaries

| Data Analyst |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 127,790.00 | $10,649.00 | $2,458.00 | $61.00 |
| 75th Percentile | $ 102,900.00 | $8,575.00 | $1,979.00 | $49.00 |
| Average | $87,640.00 | $7,303.00 | $1,685.00 | $42.00 |
| 25th Percentile | $66,300.00 | $5,525.00 | $1,275.00 | $32.00 |
| Data Engineer |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 171,801.00 | $14,316.00 | $3,303.00 | $83.00 |
| 75th Percentile | $ 145,800.00 | $12,150.00 | $2,803.00 | $70.00 |
| Average | $ 138,279.00 | $11,523.00 | $2,659.00 | $66.00 |
| 25th Percentile | $ 121,400.00 | $10,116.00 | $2,334.00 | $58.00 |
| Database Administrator |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 150,061.00 | $12,505.00 | $2,886.00 | $72.00 |
| 75th Percentile | $ 130,400.00 | $10,867.00 | $2,508.00 | $63.00 |
| Average | $ 108,448.00 | $9,037.00 | $2,086.00 | $52.00 |
| 25th Percentile | $84,800.00 | $7,067.00 | $1,631.00 | $41.00 |
| Director of Operations |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 171,801.00 | $14,316.00 | $3,303.00 | $83.00 |
| 75th Percentile | $ 143,700.00 | $11,975.00 | $2,763.00 | $69.00 |
| Average | $ 102,922.00 | $8,576.00 | $1,979.00 | $49.00 |
| 25th Percentile | $80,100.00 | $6,675.00 | $1,540.00 | $39.00 |
| Grant Writer |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $91,733.00 | $7,644.00 | $1,764.00 | $44.00 |
| 75th Percentile | $77,900.00 | $6,492.00 | $1,498.00 | $37.00 |
| Average | $70,107.00 | $5,842.00 | $1,348.00 | $34.00 |
| 25th Percentile | $55,100.00 | $4,592.00 | $1,060.00 | $26.00 |
| Director of Operations |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 171,801.00 | $14,316.00 | $3,303.00 | $83.00 |
| 75th Percentile | $ 143,700.00 | $11,975.00 | $2,763.00 | $69.00 |
| Average | $ 102,922.00 | $8,576.00 | $1,979.00 | $49.00 |
| 25th Percentile | $80,100.00 | $6,675.00 | $1,540.00 | $39.00 |
| Operations Manager |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 115,064.00 | $9,588.00 | $2,212.00 | $55.00 |
| 75th Percentile | $82,200.00 | $6,850.00 | $1,580.00 | $40.00 |
| Average | $68,498.00 | $5,708.00 | $1,317.00 | $33.00 |
| 25th Percentile | $43,500.00 | $3,625.00 | $836.00 | $21.00 |
| Policy Analyst |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 123,548.00 | $10,295.00 | $2,375.00 | $59.00 |
| 75th Percentile | $ 123,500.00 | $10,291.00 | $2,375.00 | $59.00 |
| Average | $97,464.00 | $8,122.00 | $1,874.00 | $47.00 |
| 25th Percentile | $88,000.00 | $7,333.00 | $1,692.00 | $42.00 |
| Research Associate |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $94,915.00 | $7,910.00 | $1,825.00 | $46.00 |
| 75th Percentile | $81,700.00 | $6,808.00 | $1,571.00 | $39.00 |
| Average | $71,781.00 | $5,982.00 | $1,380.00 | $35.00 |
| 25th Percentile | $57,800.00 | $4,817.00 | $1,112.00 | $28.00 |
| Senior Manager |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 178,695.00 | $14,891.00 | $3,436.00 | $86.00 |
| 75th Percentile | $ 144,800.00 | $12,066.00 | $2,784.00 | $70.00 |
| Average | $93,748.00 | $7,812.00 | $1,802.00 | $45.00 |
| 25th Percentile | $52,000.00 | $4,333.00 | $1,000.00 | $25.00 |
| Website Designer |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 109,232.00 | $9,103.00 | $2,101.00 | $53.00 |
| 75th Percentile | $84,800.00 | $7,067.00 | $1,631.00 | $41.00 |
| Average | $77,227.00 | $6,436.00 | $1,485.00 | $37.00 |
| 25th Percentile | $56,700.00 | $4,725.00 | $1,090.00 | $27.00 |
| Website Programmer |  |  |  |  |
|  | Annual Salary | Monthly Pay | Weekly Pay | Hourly Wage |
| Top Earners | $ 119,306.00 | $9,942.00 | $2,294.00 | $57.00 |
| 75th Percentile | $ 100,700.00 | $8,392.00 | $1,937.00 | $48.00 |
| Average | $85,087.00 | $7,091.00 | $1,636.00 | $41.00 |
| 25th Percentile | $67,300.00 | $5,608.00 | $1,294.00 | $32.00 |

# Appendix D —

# Appendix E — Appendix 3: Potential Funders

## Healthcare Corporations

| Or ganiz ation | Pr oduct | Links |
| --- | --- | --- |
| Adve ntist | S ponso rship Re quest | [https://hi paa-submit.jotform.com/221594871753061](https://hipaa-submit.jotform.com/221594871753061) |
| Adve ntist | Comm unity Be nefit | [https://adventisthealth.org/portland/about -us/community-benefit/](https://advent%20isthealth.org/portland/about-us/community-benefit/) |
| C ambia | He althy and Conn ected Aging | [https://www.cambiahealthfound ation.org/focus-areas/healthy-and-connected-aging.h tml](https://www.cambiahealthfoundatio%20n.org/focus-areas/healthy-and-connected-aging.html) |
| C ambia | S ponso rship | [[https://www.cambiahealthfoundation.org/applicant- resources/current-funding-opportunities.html]{.unde rline}](https://www.cambiahealthfoundation.org/appl%20icant-resources/current-funding-opportunities.html) |
| CareO regon | Comm unity G iving g rants and sp onsor ships | [https://www.careoregon.org/community/co mmunity-giving-grants-for-nonprofit-organizations](https://www.careoregon.org/community/c%20ommunity-giving-grants-for-nonprofit-organizations) |
| CareO regon | HRSN Ser vices | [re quest.social.determinants@careoregon.org](mailto:r%20equest.social.determinants@careoregon.org), |
| H ealth Share | S ponso rship | [https://www.heal thshareoregon.org/about/sponsorship](h%20ttps://www.healthshareoregon.org/about/sponsorship) |
| H ealth Share | HRSN Ser vices | [https://www.healthshareorego n.org/community-partners/hrsn](https:/%20/www.healthshareoregon.org/community-partners/hrsn) |
| H ealth Share | HRSN Ser vices | [https://health-share-or.portals.zen ginehq.com/program/community-capacity-building/info](https://health-share-or.portals.zeng%20inehq.com/program/community-capacity-building/info) |
| K aiser | HRSN Ser vices | [Laura.J.Ho ward@kp.org](mailto:Laura.J.Howard@kp.org) |
| K aiser | HRSN Ser vices | [[https://communityhealth-midatlantic.kaiserper manente.org/improving-communities/grantmaking/]{.un derline}](https://communityhealth-midatlantic.kaise%20rpermanente.org/improving-communities/grantmaking/) |
| K aiser | HRSN Ser vices | [https://communityhealth-midatlantic.kaiserpermanen te.org/wp-content/uploads/2024/02/LOI-Submitter-Hel p-Document\_508.pdf](https://communityh%20ealth-midatlantic.kaiserpermanente.org/wp-content/u%20ploads/2024/02/LOI-Submitter-Help-Document_508.pdf) |
| K aiser | HRSN Ser vices | [MedicaidHRSflexfunds@ kp.org](mailto:MedicaidHRSflexfunds@kp.org) |
| K aiser | Comm unity Be nefit | [community.benefi t@kp.org](mailto:community.benefit@kp.org) |
| L egacy | Comm unity H ealth Grant | [https://www.legacyhealth.org/Givi ng-and-Support/community-engagement/Community-Grant s](https://www.legacyhealth.org/Giving%20-and-Support/community-engagement/Community-Grants) |
| L egacy | L egacy Res earch Inst itute | [[ht tps://www.legacyhealth.org/For-Health-Professionals /legacy-research-institute/services/grants]{.underl ine}](https://www.legacyhealth.org/For-Health-Profe%20ssionals/legacy-research-institute/services/grants) |
| L egacy | S ponso rship | [https://www.legacyhealth. org/Giving-and-Support/community-engagement/Sponsor ships](https://www.legacyhealth.org/Gi%20ving-and-Support/community-engagement/Sponsorships) |
| L egacy | HRSN Ser vices | [HealthRelatedServices@pacificsource.com](mail%20to:HealthRelatedServices@pacificsource.com) |
| Ochin |  |  |
| OHSU | Comm unity P artne rship Pr ogram | [https://www.ohsu.edu/knig ht-cancer-institute/community-partnership-program-g rants](https://www.ohsu.edu/knight-can%20cer-institute/community-partnership-program-grants) |
| OHSU | Comm unity P artne rship Pr ogram | [htt ps://www.ohsu.edu/knight-cancer-institute/how-apply -community-grant](https://www.ohsu.edu%20/knight-cancer-institute/how-apply-community-grant) |
| OHSU | Comm unity P artne rship Pr ogram | [https://www.ohsu.edu/sites/ default/files/2024-01/CPP\_RFP\_2024.1\_FINAL\_lowres\_0 .pdf](https://www.ohsu.edu/sites/defau%20lt/files/2024-01/CPP_RFP_2024.1_FINAL_lowres_0.pdf) |
| OHSU | T iered G rants | [https://www.ohsu.edu/knight-ca ncer-institute/tiered-grants](https://%20www.ohsu.edu/knight-cancer-institute/tiered-grants) |
| OHSU | HRSN Ser vices | [[https://www.ohsu.edu/health-services] {.underline}](https://www.ohsu.edu/health-services) |
| OHSU | Rural Popul ation H ealth Incu bator Pr ogram | [[https://www.ohsu.edu/oregon-office-of-rural-hea lth/rural-population-health-incubator-program]{.und erline}](https://www.ohsu.edu/oregon-office-of-rura%20l-health/rural-population-health-incubator-program) |
| Pa cific S ource | Comm unity H ealth Excel lence G rants | [https://pacificsource.com /sites/default/files/2023-02/PRV510\_0123\_CHE%20Flie r.pdf](https://pacificsource.com/sites%20/default/files/2023-02/PRV510_0123_CHE%20Flier.pdf) |
| Pa cific S ource | Comm unity Ca pacit y-Bui lding Fu nding for HRSN ser vices | [https://pacificsource.com/art icle/community-capacity-building-funding-hrsn-servi ces](https://pacificsource.com/article%20/community-capacity-building-funding-hrsn-services) |
| Pa cific S ource | Comm unity H ealth Excel lence G rants | [[ht tps://www.ruralhealthinfo.org/funding/5469]{.underl ine}](https://www.ruralhealthinfo.org/funding/5469) |
| Pa cific S ource | All | [https://pacificsource.com/sites/default/fi les/2023-08/CLB1330\_0823\_PacificSource%20Funding%20 Navigation%20Guide.pdf](https://pacifi%20csource.com/sites/default/files/2023-08/CLB1330_082%203_PacificSource%20Funding%20Navigation%20Guide.pdf) |
| Pa cific S ource | Pac ificS ource Found ation for H ealth I mprov ement | [https://pacificsource.com/community/foundation?utm \_source=pdf&utm\_medium=flier&utm\_campaign=FundingGu ide&utm\_id=CLB1330](https://pacificsou%20rce.com/community/foundation?utm_source=pdf&utm_med%20ium=flier&utm_campaign=FundingGuide&utm_id=CLB1330) |
| Pa cific S ource | He althy C ommun ities Pr ogram | [[http://www.grantinterface.com/Home/Logon]{.un derline}](http://www.grantinterface.com/Home/Logon) |
| Provi dence | Comm unity G rants /Dona tions | [https://www.p rovidence.org/locations/wa/providence-regional-medi cal-center-everett/donate-and-volunteer/community-s ponsorships](https://www.providence.or%20g/locations/wa/providence-regional-medical-center-e%20verett/donate-and-volunteer/community-sponsorships) |
| Provi dence | S ponso rship | [https://webportalapp.com/sp/logi n/prmce-sponsor-application](https://w%20ebportalapp.com/sp/login/prmce-sponsor-application) |
| Provi dence | HRSN Ser vices | [HRSNBenefit@Provide nce.org](mailto:HRSNBenefit@Providence.org) |
| Tri llium | Comm unity Be nefit I nitia tives | [https://www.p rnewswire.com/news-releases/trillium-community-heal th-plan-announces-request-for-applications-for-2023 -small-grants-for-community-benefit-initiatives-301 845411.html](https://www.prnewswire.co%20m/news-releases/trillium-community-health-plan-anno%20unces-request-for-applications-for-2023-small-grant%20s-for-community-benefit-initiatives-301845411.html) |
| Tri llium | Comm unity Be nefit I nitia tives | [[https://www.trilliumohp.com/supporting-oregon-c ommunities/community-benefit-initiatives.html]{.und erline}](https://www.trilliumohp.com/supporting-ore%20gon-communities/community-benefit-initiatives.html) |
| Tri llium | Comm unity Cap acity Bui lding Fu nding | [https://www.t rilliumohp.com/supporting-oregon-communities/health -related-social-needs/community-capacity-building-f unding.html](https://www.trilliumohp.c%20om/supporting-oregon-communities/health-related-soc%20ial-needs/community-capacity-building-funding.html) |
| Ce ntral O regon H ealth Co uncil | Sta ndard G rants | [[ht tps://cohealthcouncil.org/standard-grants/]{.underl ine}](https://cohealthcouncil.org/standard-grants/) |
|  | Mini G rants | [[https://cohealthcouncil.org/mini-grants/]{.un derline}](https://cohealthcouncil.org/mini-grants/) |
| St Ch arles H ealth S ystem | Comm unity Be nefit G rants and Sp onsor ships | [[ https://www.stcharleshealthcare.org/community-healt h/community-benefit-grants-and-sponsorships]{.under line}](https://www.stcharleshealthcare.org/communit%20y-health/community-benefit-grants-and-sponsorships) |

## State Agencies

| Entity | P roduct | Links |
| --- | --- | --- |
| Oregon Health Aut hority | Block Grants | [https://www.oregon.gov/oha/hsd/amhpac/page s/block-grants.aspx](https://www.or%20egon.gov/oha/hsd/amhpac/pages/block-grants.aspx) |
| Oregon Health Aut hority | Com munity Ca pacity Bu ilding Funds | [https://www.oregon.gov/oha/hsd/medicaid-poli cy/pages/ccbf.aspx](https://www.ore%20gon.gov/oha/hsd/medicaid-policy/pages/ccbf.aspx) |
| Oregon Health Aut hority | Com munity Ca pacity Bu ilding Funds | [https://content.govdelivery.com/accounts/ORHA/ bulletins/38e15e8](https://content.%20govdelivery.com/accounts/ORHA/bulletins/38e15e8) |
| Oregon Health Aut hority | SHARE Init iative | [https://www.oregon.gov/oha/h pa/dsi-tc/pages/share.aspx](https:/%20/www.oregon.gov/oha/hpa/dsi-tc/pages/share.aspx) |
| Oregon Health Aut hority | PUBLIC HEALTH EQUITY | <https://www.oregon.gov/oha/PH/ABOUT/MODCE> T%20CBO%20Documents/PH%20Equity%20CBO%20Fiscal%2 0Guidance%20-%20AY25%20%20DRAFT-%2002.28.24.pdf> |
| Oregon Health Aut hority | PUBLIC HEALTH EQUITY | [https://content.govdelivery.com/accounts/ORHA/ bulletins/37611cc](https://content.%20govdelivery.com/accounts/ORHA/bulletins/37611cc) |
| Oregon Health Aut hority | GRANT | [https://www.oregon.gov/oha /ph/healthypeoplefamilies/youth/healthschool/sch oolbasedhealthcenters/pages/mh-expansion-grant.a spx](https://www.oregon.gov/oha/ph/%20healthypeoplefamilies/youth/healthschool/schoolb%20asedhealthcenters/pages/mh-expansion-grant.aspx) |
| Oregon Health Aut hority | HTO CHIP P roject Grants | [https://www.oregon .gov/oha/PH/ABOUT/Documents/HTO%20CHIP%202024%20 FAQ.pdf](https://www.oregon.gov/oha%20/PH/ABOUT/Documents/HTO%20CHIP%202024%20FAQ.pdf) |
| Oregon State | I MPACTS Grant P rogram | [https://ww w.oregon.gov/cjc/impacts/Documents/2020\_IMPACTSO nePager.pdf](https://www.oregon.gov%20/cjc/impacts/Documents/2020_IMPACTSOnePager.pdf) |

## Foundations and Trusts

| Foun dation | P roduct | Links |
| --- | --- | --- |
| Car penter Foun dation | Grant | [http://carpenter-foundation.or g/](http://carpenter-foundation.org/) |
| Anna May Family Foun dation | Grant | [http://www.a nnamay.org/](http://www.annamay.org/) |
| Gordon Elwood Foun dation | Grant | [[http s://www.gordonelwoodfoundation.org/index]{.underli ne}](https://www.gordonelwoodfoundation.org/index) |
| Ma ybelle Clark Mac donald Fund | Grant | [https://mcmfundgiving.org/grants /](https://mcmfundgiving.org/grants/) |
| M J M urdock Char itable Trust | STR ATEGIC GRANT | [https://murdocktru st.org/grant-application-process/](ht%20tps://murdocktrust.org/grant-application-process/) |
| C ollins Foun dation | Resp onsive Grant | [https://www.collinsfou ndation.org/responsive-grantmaking-submission-guid elines](https://www.collinsfoundation%20.org/responsive-grantmaking-submission-guidelines) |
| C ollins Foun dation | Resp onsive Grant | [https://www.collinsfoundat ion.org/responsive-grantmaking-submission-guidelin es/frequently-asked-questions](https:%20//www.collinsfoundation.org/responsive-grantmaking%20-submission-guidelines/frequently-asked-questions) |
| Benton Com munity Foun dation | Com munity Grants | [https://bcfgives .org/wp-content/uploads/2024/02/2023-Full-Grant-Hi story.pdf](https://bcfgives.org/wp-co%20ntent/uploads/2024/02/2023-Full-Grant-History.pdf) |
| Reser Family Foun dation | Resp onsive Grant Pr ograms | [https://thereserfamilyfoun dation.org/apply-for-a-grant/](https:%20//thereserfamilyfoundation.org/apply-for-a-grant/) |
| Foster Foun dation | Grant | [[ht tp://www.thefosterfoundation.org/Home.htm]{.underl ine}](http://www.thefosterfoundation.org/Home.htm) |
| Doug Flutie Foun dation | Autism Com munity Impact Grant | [https://flutiefoundation .org/helping-communities/autism-community-impact-g rant/](https://flutiefoundation.org/h%20elping-communities/autism-community-impact-grant/) |
| Doug Flutie Foun dation | Flutie F ellows – Career and Life Goal S upport | [[ht tps://flutiefoundation.org/helping-individuals/flu tie-fellows-career-and-life-goal-support/]{.underl ine}](https://flutiefoundation.org/helping-individ%20uals/flutie-fellows-career-and-life-goal-support/) |
| Doug Flutie Foun dation | Fin ancial Relief for Fa milies | [https:// flutiefoundation.org/helping-families/direct-finan cial-support/](https://flutiefoundati%20on.org/helping-families/direct-financial-support/) |
| Ch ambers Family Foun dation | Grant | [https://www.chambers familyfoundation.com/submissions](htt%20ps://www.chambersfamilyfoundation.com/submissions) |
| Meyer Me morial Trust | Grant | <https://mmt.org/> |
| Ben B Cheney Foun dation | Grant | [[https://www.benbcheneyfoundation.org/]{. underline}](https://www.benbcheneyfoundation.org/) |
| Autzen Foun dation | Grant | [[ https://www.autzenfoundation.org/deadlines]{.under line}](https://www.autzenfoundation.org/deadlines) |
| Oregon Com munity Foun dation | Grant | [https://oregoncf.org /grants-and-scholarships/grants/](htt%20ps://oregoncf.org/grants-and-scholarships/grants/) |
| Robert Wood J ohnson Foun dation | Mu ltiple | [[https://www.rwjf.org/en/grants.html] {.underline}](https://www.rwjf.org/en/grants.html) |
| Robert Wood J ohnson Foun dation | Mu ltiple | [https://www. rwjf.org/en/grants/active-funding-opportunities.ht ml?o=1&us=1](https://www.rwjf.org/en/%20grants/active-funding-opportunities.html?o=1&us=1) |
| Weyer houser | Giving Fund | [ht tps://www.weyerhaeuser.com/company/values/citizens hip/giving-fund/](https://www.weyerha%20euser.com/company/values/citizenship/giving-fund/) |

# Appendix E —

# Appendix F — Appendix 4: Neurodiversity and Neurodivergence

Many people find [this article](https://neuroqueer.com/neurodiversity-terms-and-definitions/) by Dr. Nick Walker to be the definitive overview of these terms and how they are used and misused. We put together the summary below with the help of [chatGPT](https://chatgpt.com/share/e60ffdec-5945-45d2-9a14-2abe39cf4f8d):

## Neurodiversity (concept)

**Definition:** Neurodiversity is the idea that neurological differences, like autism, ADHD, dyslexia, and others, are natural variations of the human genome. This concept emphasizes that these differences should be recognized and respected as a part of human diversity.

**Historical and Social Context:** The term “neurodiversity” was coined in the late 1990s by sociologist Judy Singer. It arose from the disability rights movement and the autistic rights movement, which sought to challenge the medical model of disability that views neurological differences as deficits or disorders to be cured. Instead, neurodiversity advocates promote acceptance and understanding, emphasizing the strengths and contributions of neurodivergent individuals.

## Neurodiversity (paradigm)

**Definition:** The neurodiversity paradigm is a framework that challenges traditional views of neurological differences. It posits that these differences should be seen as normal variations rather than abnormalities or deficits. This paradigm promotes the idea that society should adapt to accommodate these differences rather than forcing individuals to conform to a neurotypical standard.

**Historical and Social Context:** This paradigm shift gained momentum in the early 2000s, aligning with broader social movements advocating for civil rights and inclusion. It has influenced fields like education, employment, and healthcare, encouraging practices that support diverse ways of thinking and learning.

## Neurodiversity (movement)

**Definition:** The neurodiversity movement is a social movement that advocates for the rights and inclusion of neurodivergent individuals. It seeks to promote understanding, acceptance, and accommodation of neurological differences. The movement has worked to reframe autism as a minority identity rather than a disorder.

**Historical and Social Context:** Emerging in the late 20th century, the neurodiversity movement has been driven by self-advocates and allies. It challenges stigmatizing narratives and calls for systemic changes in how neurodivergent individuals are treated in society. This movement has led to increased visibility and advocacy for policies that support neurodiversity in schools, workplaces, and communities.

## Neurodivergence

**Definition:** Neurodivergence refers to the state of having a brain that functions differently from the typical standards of society. It is an umbrella term that includes various neurological conditions like autism, ADHD, dyslexia, and more.

**Historical and Social Context:** The term “neurodivergence” gained prominence alongside the neurodiversity movement. It helps to create a more inclusive language that recognizes the spectrum of neurological differences without implying pathology. This shift in terminology supports a more positive and accepting view of diverse cognitive profiles.

## Neurodivergent

**Definition:** Neurodivergent describes individuals whose neurological development and functioning are atypical. This term is used to identify people who have conditions like autism, ADHD, dyslexia, etc.

**Historical and Social Context:** The adoption of the term “neurodivergent” reflects a growing acceptance of diversity in neurological functioning. It emphasizes identity and self-advocacy, allowing individuals to claim their differences as part of who they are rather than as something to be fixed or hidden.

## Neurotypical

**Definition:** Neurotypical refers to individuals whose neurological development and functioning are considered standard or typical by societal norms. It is often used in contrast to neurodivergent.

**Historical and Social Context:** The term “neurotypical” originated within the neurodiversity community as a way to distinguish between those who conform to societal norms of neurological functioning and those who do not. It highlights that “typical” neurological functioning is not the only valid or acceptable way of being, promoting a more inclusive view of human diversity.

### **References**

1. Singer, J. (1998). **Odd People In: The Birth of Community Amongst People on the ‘Autistic Spectrum’**. Honours Thesis, University of Technology, Sydney.

2. Silberman, S. (2015). **NeuroTribes: The Legacy of Autism and the Future of Neurodiversity**. Avery.

3. Armstrong, T. (2010). **Neurodiversity: Discovering the Extraordinary Gifts of Autism, ADHD, Dyslexia, and Other Brain Differences**. Da Capo Lifelong Books.

4. Kapp, S. K., et al. (2013). **Deficit, Difference, or Both? Autism and Neurodiversity**. Developmental Psychology, 49(1), 59–71.